## Sheet1
TASK NUMBER | TASK NAME | DURATION | RESOURCES
PHASE 1 | PROJECT INITIALIZATION
1.1 | INITIALIZE | (Sep 2- Sep21)
1.1.1 | Identify MOV | 2days
1.1.2 | DESIRED AREAS OF IMPACT | 2days
1.1.3 | DESIRED VALUE OF IMPACT | 1 day
1.1.4 | DEFINING ALTERNATIVES | 5 days
1.1.5 | ANALYSIS OF ALTERNATIVES | 2days
1.1.5.1 | TOTAL COST OF OWNERSHIP | 3days
1.1.5.2 | TOTAL BENEFIT OF OWNERSHIP | 2days
1.1.6 | BUSINESS CASE DELIVERABLE | 1day(sep 20)
1.1.7 | MILESTONE : CLIENT APPROVAL OF BUSINESS CASE | 1day(Sep21)
PHASE 2 | PROJECT CHARTER AND PROJECT PLAN
1.2 | PLANNING | sep 26 to Oct 11th
1.2.1 | IDENTIFY SCOPE OF PROJECT | 1day
1.2.2 | ESTIMATING THE BUDGET | 2 days
1.2.2.1 | COST BENEFIT ANALYSIS | 2days
1.2.2.2 | NPV, ROI AND PAYBACK | 2days
1.2.3 | DEFINE SCOPE MANAGEMENT PLAN | 1day
1.2.4 | IDENTIFY and ALLOCATE THE RESOURCES | 1day
1.2.5 | DESIGNING THE STRUCTURE CHART (use case Diagram after this) | 1 Day (Sep-28)
1.2.6 | CREATING THE WORK BREAKDOWN STRUCTURE | 3 days
1.2.7 | DELIVARABLE : SCOPE MANGEMENT PLAN | 1day
1.2.8 | MILESTONE: SCOPE MANAGEMENT PLAN APPROVAL | 1day
PHASE 3 | PROJECT EXECUTION
1.3 | EXECUTE
1.3.1 | ANALYSIS | 21 days
1.3.1.1 | ANALYZING THE CURRENT SYSTEM | 2 days
1.3.1.2 | REQUIREMENT GATHERING | 2 days
1.3.1.3 | ANALYZE THE REQUIREMENTS | 2 days
1.3.1.3.1 | ANALYZE WIRED NETWORKS | 1 day
1.3.1.3.2 | ANALYZE WIRELESS NETWORKS | 2 days
1.3.1.3.3 | ANALYZE WORKSTATIONS | 2 days
1.3.1.3.4 | ANALYZE SERVERS | 2days
1.3.1.3.5 | ANALYZING BACKUP SERVERS | 2 days
1.3.1.3.6 | ANALYSING THE PHONE SYSTEM | 2 days
1.3.1.3.7 | ANALYZE THE SURVELLIANCE SYSTEM | 2 days
1.3.1.4 | ASSIGN THE TEAM | 1 day
1.3.1.5 | CLIENT APPROVAL | 1 day
1.3.2 | DESIGN
1.3.2.1 | DEVELOPING ICT | 2days
ARCHITECTURAL DESIGN
| CLIENT APPROVAL | 1day
1.3.4 | IMPLEMENTATION (Constructiing the new system) | 15 days
1.3.4.1 | UPGRADING WIRED NETWORKS - REPLCAING 2 SWITCHES / YEAR | 1day
1.3.4.2 | UPGRADING WIRELESS NETWORKS - REPLACING 5 ROUTERS /YEAR | 1 day
1.3.4.3 | REPLACING WORKSTATIONS
1.3.4.3.1 | DESKTOP REPLACEMENTS - 5 / YEAR ( go in parallel) | 1 day
1.3.4.3.2 | LAPTOP REPLACEMENTS - 5/ YEAR | 1 day
1.3.4.4 | REPLACING SERVERS - REPLACING 3 SERVERS , 1 PER 20 MONTHS | 1 day
1.3.4.5 | MIGRATING BACKUP STORAGE FROM ONPREMISE TO CLOUD | 5 days
1.3.4.6 | PHONE SYSTEM REPLACEMENT | 2 days
1.3.4.7 | UPGRADING CAMERA SURVEILLANCE SYSTEM | 2 days
1.3.4.8 | CLIENT APPROVAL | 1 day
1.3.5 | INTEGRATION AND TESTING | 20 days
1.3.5.1 | INTEGRATION
1.3.5.1.1 | CONFIGURING SWITCHES INTO NETWORKS | 1 days
1.3.5.1.2 | CONFIGURING WIRELESS ROUTERS INTO NETWORKS | 1 day
1.3.5.1.3 | INSTALLING SOFTWARES IN REPLACED DESKTOPS | 1 days
1.3.5.1.4 | INSTALLING SOFTWARES IN REPLACED LAPTOPS | 1 days
1.3.5.1.5 | SERVER MIGRATION | 2 days
1.3.5.1.6 | BACKUP STORAGE MIGRATION TO CLOUD | 5 days
1.3.5.1.7 | INSTALLING NEW PHONE SYSTEM | 2 days
1.3.5.1.8 | INSTALLING THE NEW CAMERA SYSTEM | 2 days
1.3.5.2 | TESTING
1.3.5.2.1 | DEVELOP A TEST PLAN | 2 days
1.3.5.2.2 | DEFINE TEST CASES | 2 days
1.3.5.2.3 | HARDWARE AND SOFTWARE TESTING | 1 da
1.3.5.2.3.1 | TESTING THE SWITCHES CONNECTIVITY | 0.5 days
1.3.5.2.3.2 | TESTING THE WIRELESS ROUTER CONNECTIVITY | 0.5 day
1.3.5.2.3.3 | TESTING NEW DESKTOPS | 1 day
1.3.5.2.3.4 | TESTING NEW LAPTOPS | 1 day
1.3.5.2.3.5 | SERVER APPLICATION SOFTWARE TESTING | 1day
1.3.5.2.3.6 | DATABASE SERVER MIGRATION TESTING | 1 day
1.3.5.2.3.7 | PERFORM TESTING FOR BACKUP DATA ON CLOUD | 2 day
1.3.5.2.3.8 | TESTING TELECOMMUNICATION CONNECTIVITY | 1day
1.3.5.2.3.9 | TESTING THE NEW CAMERA SYSTEM OPERABILITY | 1day
1.3.5.2.4 | SYSTEM TESTING | 2 days
1.3.5.2.4.1 | USABILITY TESTING | 1 day
1.3.5.2.4.2 | SECURITY TESTING | 3 days
1.3.5.2.5 | PERFORMANCE TESTING | 3 days
1.3.5.2.6 | ANALYZING THE TEST RESULTS | 1 day
1.3.5.2.7 | CLIENT APPROVAL | 1 day
1.3.6 | MAINTAINANCE AND SUPPORT
1.3.6.1 | Developing Maintenance plan | 2days
1.3.6.2 | SYSTEM MAINTAINANCE | 1 day
1.3.6.3 | POST IMPLEMENTATION REPORT | 1day
1.3.6.4 | SUPPORT SELECTION - identifying the areas of support to be provided | 1 day
1.3.6.5 | PLANNING A TRAINING PROGRAM | 1 day
1.3.6.6 | CONDUCTING THE TRAININGS | 2 days
1.3.6.7 | DOCUMENTATION | 2 days
1.3.6.8 | MILESTONE - APPROVAL OF PROJECT EXECUTION | 1 day
PHASE 4 | PROJECT CLOSURE | 5days
1.4 | CLOSE PROJECT
1.4.1 | PREPAE PROJECT REPORT AND PRESENTATION | 2 days
1.4.2 | PREPARE ANNUAL REPORT | 2 days
| MILESTONE - APPROVAL OF PROJECT REPORT | 1 day
PHASE 5 | PROJECT EVALUATION | 0 days
1.5 | EVALUATING THE PROJECT SUCCESS
1.5.1. | CONDUCTING SURVEYS
1.5.1. | PROJECT TEAM EVALUATION